## Slide 1
TECHNICAL WORKING GROUP
Mr. Andi Rusandi
SESSION 10.3 : MARINE PROTECTED AREAS (MPA) TECHNICAL WORKING GROUP
Chair of CTI-CFF MPA WORKING GROUP

## Slide 2: Meeting outline
Focal point of MPA Working Group
Update Numbers and Area of MPA in The Coral Triangle
Status of Workplan for 2019
Update and Deliberation of SOM-14 Decisions
Proposed MPA workplan for 2020
Agreement on SOM-15 recommendations

## Slide 3: 1. Focal point of MPA Working Group
Country | Focal Point
Indonesia (Chair) | Mr. Andi Rusandi, Director for Marine Conservation and Biodiversity Ministry of Marine Affairs and Fisheries Mr. Amehr Hakim, Deputy Director for Marine Protected Areas Designation
Malaysia | Ms. Rimi Repin, Assistant Director of Research and Education Division, Sabah Parks Alternate Focal Point: Mr. Adam Malik bin Masidi
Papua New Guinea | Ms. Yvonne Tio, Executive Manageress Marine, SMED CEPA Alternate focal Point: Mr. Bernard Kombeng Suruman
Philippines | Asec Ricardo L. Calderon, Director of the Biodiversity Management Bureau Department of Environment and Natural Resources
Solomon Islands (Co-Chair) | Mr. Peter Kenilorea, Chief officer Community Based resource Management Section, Ministry of Fisheries and Marine Resources Alternate: Mr Trevor Maeda, Principal Conservation Officer, Ministry of Environment, Climate change, Disaster Management and Meteorology
Timor Leste | Mr. Orlando Halek Kalis, Chief of Department of Fishing Port, Ministry of Agriculture and Fisheries Alternate: Mr. Fidelino Sousa Marques, Senior Staff, National Director Fisheries and Marine Resource Management, Ministry of Agriculture and Fisheries.

## Slide 4: 2. Update Numbers and Area of MPA in The Coral Triangle
CT Country | Total Numbers of MPAs 2019 (National) | Total Area of MPAS (Km²) | Contribution MPAs In CT Area | Total Area of MPAS (Km²)
Indonesia | 195 | 226,800 Km² | 117 | 162,600 Km²
Malaysia | 65 | 15,100.37 km2 | 4 MPA (Sabah) | 9,523.63 km2 (Total)
Papua New Guinea | 87 (Locally Managed) | 2032.17 km2 | 87 (Locally Managed) | 2032.17 km2
Philippines | 1,800+ (Locally Managed) 73(National Managed) | 33825.78km2 (National Managed) | 1,800+ (Locally Managed) 72 (National Managed) | 33825.78km2 (National Managed)
Solomon Islands | 290+ (Locally Managed 2012) 1 (National Managed) | 1,819 km2 | 290+ (Locally Managed 2012) 1 (National Managed) | 1,819 km2
Timor Leste | 22 | 194.63 Km² | 22 | 194.63 Km²
Region | 2532 | 231,195 | 2371 | 166,995

## Slide 5: 3. MPAWG Status of Workplan for 2019
NO | Actions Plan | Average Regional Status | Country Status |  |  |  |  |  | annotations
 |  |  | ID | MY | PNG | PL | SI | TL | 
1 | 8th MPA REX and 8th MPA TWG meeting | 100% (done 16-19 Oc2019) | √ | √ | √ | Not attend to the meeting | √ | √ | Successfully held in Sabah, Malaysia on 16-19 oct 2019
2 | Regional Recognition/Awards of best managed MPAs. | Nomination base from Categories 3 and 4 CTMPAS | √ | √ | √ | √ | √ | √ | Used previous data of 2nd round CTMPAS
3 | Constitute and operationalize the SMT-TF | 90% | √ Submitted to RS | Waiting for nominees | Waiting for nominees | Waiting for nominees | √ Submitted to RS | √ Submitted to RS | Indonesia and Timor Leste were submitted and presented the Task Force of sustainable Tourism during the 8th Rex
4 | SMT-TF to develop/refine the criteria, indicator and brand for sustainable marine tourism in the CT. | 100% Design and socialization) | √ | √ | √ | √ | √ | √ | TOR of ST is available In attachment 2
5 | Capacity building for CT Atlas Focal Points. | 100% | √ | √ | √ | √ | √ | √ | CT6 Country has given the focal points name of CT Atlas, First socialisation held the 8th MPA Rex
6 | 3rd Round of CTMPAS nomination | On Progress, | √ | √ | √ | √ | √ | √ | Data on progress to submit to CT-ATLAS
7 | Management of MPAs in the CT6. | 90% | √ Reported on MPA Rex | √ Reported on MPA Rex | √ Reported on MPA Rex | Not attend to the meeting | √ Reported on MPA Rex | √ Reported on MPA Rex | CT6 Country was presented the Progress and update of MPA management in the 8th MPA Rex

## Slide 6: 4. Update and Deliberation of SOM-14 Decisions
NO | Actions Plan | Average Regional Status | Country Status |  |  |  |  |  | Annotations
 |  |  | ID | MY | PNG | PL | SI | TL | 
1 | Endorse for implementation of the 2019 Workplan; | 100% | √ | √ | √ | √ | √ | √ | * Please See Workplan 2009 on the next slide
2 | Urge the Regional Secretariat to prioritize the reactivation of the CT Atlas; | 100% , Socialisation and 1st Training | √ agree | √ agree | √ agree | √ agree | √ agree | √ agree | The CTAtlas website 2.0 has introduced in the 8th MPA Rex and other CTI event
3 | Request the Regional Secretariat and/or partners to support and secure funding sources for the engagement of an experienced MPA Coordinator immediately; | 100% (done by RS facilitators) | √ agree | √ agree | √ agree | √ agree | √ agree | √ agree | The RS-CTI was enhanced the capacity of internal human resource to support TWG
4 | Acknowledge with appreciation the support of USAID SEA Project-Indonesia, CTC, WWF, CI and NOAA in the 7th MPA REX particularly on Sustainable Marine Tourism; | 100% | √ | √ | √ | √ | √ | √ | Letter of Appreciation was sent to the partners to acknowledge their continues support to the MPA WG
5 | Acknowledge the progress and updates on MPA management of the CT6 Countries; | 100% (done 16-19 Oc2019) | √ | √ | √ | √ | √ | √ | * Please See Workplan 2009 on the next slide
6 | Recognize the need for sustained efforts to strengthen capacity building on MPA management including Sustainable fisheries; | 100% (done 16-19 Oct 2019) | √ | √ | √ | √ | √ | √ | The MPA for sustainable fisheries has presented by WWF Indonesia and Stacey Tighe as resources person in the 8th MPA Rex
7 | Recognize the need to conduct research and development to generate information, technologies and methodologies to support effective MPA management | On Progress, Look the opportunities | √ agree | √ agree | √ agree | √ agree | √ agree | √ agree | Approach by see the opportunity to cooperate with Universities, research institutions. and development Partners
8 | Endorse CTMPAS nominations as among the priorities in CT6 countries | 100% | √ Use CTMPAS and CT ATLAS data | √ Use CTMPAS and CT ATLAS data | √ Use CTMPAS and CT ATLAS data | √ Use CTMPAS and CT ATLAS data | √ Use CTMPAS and CT ATLAS data | √ Use CTMPAS and CT ATLAS data | Remind NCC to submit CTMPAS nomination

## Slide 7
Planned Activities | Time Frame | Projected Budget | Source of Budget
9th MPA REX and 9th MPA TWG Meeting in Papua New Guinea | Q3 (Jul – Sept) | USD50,000 | Regional Secretariat, Development Partners and Host Country
Completion of CTMPAS Certification Process for Cat 1, 2, and 3 | Q1 (Jan – Mar) | Not need budget | 
CT Atlas Training | Q1(Jan– Mar) |  | Regional Secretariat (CT Atlas project)
Sustainable Marine Tourism final design and launch pilot sites | Q3 (Jul– Sept) |  | Through Virtual Communication and NCC Activities
Develop activities that integrate with other TWG in Priority MPA Sites | Q1 – Q4 (Jan – Dec) |  | 
Participate in International Coral Reef Initiatives Event | Q1 – Q2 (Jan – Jun) |  | Regional Secretariat (subject to availability of funds)
5. Proposed MPA Workplan for 2020

## Slide 8
6. Agreement on SOM-15 recommendations
Acknowledged the efforts of the CT6 countries and the Development Partners on the status of the SOM-14 decisions;
Acknowledged the countries that have submitted the nominees for Sustainable Marine Tourism Focal Points, Pilot community sites and encourage other countries to submit their nominees;
Encouraged NCC to socialize with national counterparts the destination development programs and criteria from the Global Sustainable Tourism Council (GSTC) for potential application in their national pilot sites, and provide brief report to Regional Secretariat
Tasked the Regional Secretariat and Sustainable Marine Tourism Task Force to provide support in the preparation of a guideline or outline for the concept paper of a joint roadmap of sustainable tourism for five years at prioritized community sites, and phasing into larger sites;
Requested all NCCs to complete their data inputs to the CT Atlas in preparation for the CT Atlas training in the First Quarter of 2020.
Recommended for the formal certification of Category 1, 2, 3 and 4 be done every two years at SOM

## Slide 9
7. Requested NCCs to nominate the external advisors who will review the CTMPAS Category 3 and 4 sites;
8. The MPA TWG recommended that the next steps in strengthening the CTMPAS is to:
  develop pilot activities in community sites in CT6 member countries that integrate with other Technical Working Groups and Cross Cutting Initiatives in the priority Seascapes;
  develop awareness and capacity in the CT6 member countries on the use of MPA networks as a tool for designing and integrating Category 3 and 4 MPAs with the prioritized roadmaps from EAFM, Threatened Species and Climate Change Adaptation Technical Working Groups for next operational steps in the priority Seascapes; and
  complete the design of CTMPAs award program to first be launched in 2021 at the next SOM in connection with the reverification of the CTMPAS inventory.
9. Supported the Recommendation of the MPA to turn over the Chair from Indonesia to Solomon Islands and the turn over of the Co-Chair from Solomon Islands to Timor Leste based on the provisions stipulated in the Rules of Procedures of the MPA WG;
10. Endorsed the MPA TWG Workplan for 2020.
Agreement on SOM-15 recommendations