## Slide 1
SOM14
14th Senior Officials’ Meeting
12 - 13 December 2018
Manila, Philippines
SESSION 8: TECHNICAL WG
Vagi Rei
Chair of CTI-CFF Threatened Species Working Group
Threatened Species Working Group

## Slide 2: Outline
Focal Point
Partners
Decision Endorsed on SOM 13 and its Status
Status on TSWG Work Plan 2018
Activities of TSWG 2018
Status of Accomplishment of Priority Activities
Challenges
Work Plan for 2019
Recommendation for SOM 14

## Slide 3: Focal Point
Member Country | Focal Point
Indonesia (Co-Chair) | Andi Rusandi, Director for Marine Conservation and Biodiversity, MMAF Supported by: Mr Firdaus Agung
Malaysia (Malaysia) | Deputy General Director, Department of Fisheries Malaysia Supported by Mr. Ab. Rahim Gor Yaman
Papua New Guinea (Chair) | Mr. Vagi Rei, Manager Conservation and Environment Protection Agency Supported by Lulu Osembo, Elton Kaicokai
Philippines | Crisanta Marlene Rodriguez, Director, Biodiversity Management Bureau, DENR Supported Pablo delos Reyes, Jr and Ludivina L Labe
Solomon islands | Ivory Akao, Ministry of Fisheries and Marine Resources Supported by: Agnetha Vave-Karamui, Chief Conservation Officer, MECDM
Timor-Leste | Pedro Pinto, Ministry of Agriculture and Fisheries Supported by: Junior Pascoal de Carvalho

## Slide 4: Partners
Role | Primary Partners
Technical Lead | World Wide Fund for Nature (WWF)
Coordination Support | Regional Secretariat
Technical Support | GIZ, Conservation International Philippines, SEAFDEC

## Slide 5: Status on Decisions Endorsed by SOM 13
Decision Endorsed from SOM 13 | Status
Recognized the achievement of the Sulu-Sulawesi Seascape Project in establishing the first network of MPAs in the Philippine side of the transboundary MTPAN as safe havens for the Green Turtles (Chelonia mydas); | Completed
Tasked the Sulu-Sulawesi Seascape Project to include the Transboundary MPA Network for Marine Turtles in the regional conservation plan for marine turtles and for the Project through the Regional Secretariat coordinate with TSWG for the next steps; | Initiated the development for the regional conservation plan for marine turtles that recognise Transboundary MPA Network as one of the strategic actions in the region
Noted the progress made by the countries in formulating their national conservation plans for marine mammals, sharks and rays and marine turtles, thus, tasked the WG to put together a region-wide conservation plan for these threatened species; | Working in progress. The countries have made good progress, while others are finalising their National Conservation plans. TSWG will need to Plan a write shop plan to pull together a region-wide conservation plan

## Slide 6: Status on Decisions Endorsed by SOM 13
Decision Endorsed from SOM 13 | Status
Supported the recommendation of the TSWG to turnover the Chairmanship from Malaysia to Papua New Guinea and for Indonesia as Co-Chair based on the provisions stipulated in the TSWG Terms of Reference; | Done
Tasked the Working Group to finalize the proposed Terms of Reference for the creation of a pool of experts on threatened species | The TOR finalised and approved during the 2nd Threatened Species working group meeting. Document circulated to all NCCs. Next step to have it endorsed by SOM 14
Noted the progress of the TSWG to plan the development of the TSWG monitoring and evaluation indicators | Already discussed in 1st REX TSWG in Manila in April 2018. RS has circulated the report to CT6 for Feedback in 2019 first quarter
Endorsed the implementation of the 2018 TS Work Plan and to call on the partners and collaborators to continue to provide technical and financial support to Goal 5. | Done

## Slide 7: Status on TSWG Work Plan 2018
Planned Activities | Status
Finalization of TOR for a pool of experts on threatened species | Done
Draft the M&E Indicators for TS | To be finalized
Identification training on sharks and rays | Postponed to 2019 due to RS transition
Write shop on the formulation of the Region-wide Conservation Plan for Marine Mammals, Sea Turtles and Sharks and Rays | Postponed to 2019 due to RS transition
Conduct IUCN Red List workshop ( Sharks and Rays) | Subject to schedules for IUCN at the global level and for CTI region in 2020
Write shop on the development of the Region-wide Assessment Report on Threatened Species (Marine Mammals, Sea Turtles, Sharks and Rays) | Initial gathering of available data and information and submitted to RS. Postponed for 2019 (Need technical support)
Production of maps identifying confirmed locations and migratory routes of the threatened species | Postponed to 2019 for each country to submit its specific species (e.g. Sea turtle) to RS then RS to WWF-ID
Annual TS TWG Meeting | Done

## Slide 8: Activities of TSWG 2018
Activities | Date | Venue
1st Threatened Species Working Group Regional Exchange | 24-26 April 2018 | Quezon City, Philippines
2nd CTI threatened species Technical Working Group Meeting | 26 April 2018 | Quezon City, Philippines

## Slide 9: Status of Accomplishment of Priority Activities
Goal 5: Threatened Species Status Improving | 
Target 1: Improved status of sharks, sea turtles, seabirds, marine mammals, corals, seagrass, mangroves and other identified threatened species. | Status
Conduct regional exchanges to complete the Conservation Action Plans for sharks, marine turtles, marine mammals and sea birds. TSWG agreed to include rays. | Started
Undertake baseline assessments of existing initiatives on the conservation and management of sharks, marine turtles, seabirds, marine mammals, corals, seagrass, mangroves. | Ongoing
Expand implementation of the SSME Comprehensive Action Plan for charismatic, threatened and migratory species to the CTI | Ongoing
Initiate sustainable financing and partnership-building for the implementation of the above-mentioned action plans | Ongoing
Finalize and endorse indicators for TSWG | Ongoing and just need to finalise

## Slide 10: Challenges
Funds to support the activities in the Regional level e.g. Write shop
Technical assistance and support in the developing/writing of the region-wide assessment report and conservation plan for TS (marine mammals, sharks and rays and sea turtle) in the coral triangle areas

## Slide 11: Work Plan 2019
Activities | Time Frame | Projected Budget | Source of Budget
Identification training on sharks and rays | February | WCS/ NCC Indonesia will cover: 1) accommodation. 2) meals; 3) local transportation; 4) fieldtrip; 5) Resource Person and materials | Airfares and per diem to organise by RS
Hold the annual TSWG meeting back to back with the write-shop to finalize the M&E Indicators for TS/on the development of the Region-wide Assessment Report on Threatened /on the formulation of the Region-wide Conservation Plan for Marine Mammals, Sea Turtles and Sharks and Rays | April -May | $24000 allocated by RS | From RS and Development partners
Production of maps identifying the locations and migratory routes of the threatened species ( CT6 to submit to RS ) | 3rd quarter |  | Technical support by WWF -Indonesia
Finalise the TOR of the TSWG | 3rd quarter |  | No Budget needed

## Slide 12: Recommendation for SOM-14 Consideration
Note the progress of the TSWG to develop the Regional Conservation Plan of Threatened Species (sharks, rays and sea turtles and marine mammals);
Endorse TOR for pool of experts on threatened species as well as the list of pool of experts;
Note and urge countries to move forward in formulating the assessment report on Threatened Species and also developing the national conservation plan for marine mammals, sea turtles, shark and rays;
Note and urge countries to move forward in formulating the threatened species monitoring and evaluation indicators;
To recognize the need for Regional Secretariat and/or Partners to support and secure funding sources for the engagement of an experienced TSWG coordinator;
Acknowledge the support of the German BMU through GIZ and CI to the TSWG in producing a draft outline of the regional conservation plan for sea turtles and other priority threatened species;
Endorse the work plan for TSWG for calendar year 2019;

## Slide 13
Terima Kasih - Maraming Salamat Tank Iu- Obrigado Tagio Tumas
Photo credits: Pixabay & IYOR Bank/JayneJenkins/FabriceDudenhofer/Yen-YiLee