## Slide 1
Monitoring and Evaluation Working Group (MEWG)
Ms. Noor Afifah Abdul Razak
Chair of MEWG
November 2022

## Slide 2: Update on MEWG Workplan and Budget for 2022
Activities | Time frame | Budget (Online) | Update
Monitoring & Evaluation Working Group (online meeting) | Q2-Q3 | 900 | Conducted on October 28, 2022
M&E training | Q2-Q3 | 600 | Conducted on October 28, 2022
RPOA 2.0 - Drafting of the text of RPOA 2.0 | Q2- Q3 | 28,400 | Done. 2 In-Situ Writeshops have been conducted: June 7-8, 2022 September 21-22, 2022
CT Atlas | Q2-Q3 | 1,920 | Concept note by SUFIA PSE Allen Coral Atlas ATSEA 2
Training on Knowledge Management System and Set-up and organize an efficient Knowledge Management System for Documents and Records Management and Storage | (Feb/March 2022-TBC) | Supported by SUFIA | Done. June 21, 2022. (Supported by SUFIA LCD)
Training on Program and Activity Results Reporting and Communication, including Gender Sensitive Reporting | (April 2022-TBC) | Supported by SUFIA | Done. April 19, 2022 and April 25, 2022. (Supported by SUFIA LCD)
Training on MEL Data Management and Designing and Conducting Value-Added Research/Develop MEL Data Management Manual including Procedures to monitor and evaluate project performance and achievements | (May 2022-TBC) | Supported by SUFIA | Done. June 22, 2022. (Supported by SUFIA LCD)
GIS training (re: for CT Atlas) – | TBC | Supported by SUFIA | 

## Slide 3: MEWG Workplan and Proposed Budget for 2023
Activities | Time frame | Budget
Monitoring & Evaluation Working Group- Physical meeting, and the Monitoring and Evaluation training- Physical training. (Propose to be conducted in Pacific Countries, TBD in SOM 17) | Q2 | USD 8,500
RPOA 2.0 M&E Plan Framework (upon receive the data from CT6 then the M&E Plan Framework will be finalized) Online meeting prior – Physical meeting for finalization | Q1 | 
CT Atlas – Track the progress Training and Discussions | Q2-Q3 | USD 8,500
GIS training (re: for CT Atlas) – |  | 
Activities from RPOA 2.0 Implement of M&E activities Development of a priority regional score card and dashboard Access and full operation of CT Atlas as an updated platform for regional information/data and for tracking implementation of the RPO 2.0 |  | RS will further discuss to get financial support from fund available from partners or future global fund which is currently peruse by RS