## Slide 1: CTI-CFF PPP Preparation
Expert Consultation Meeting
Milestones

## Slide 2: Timeline

## Slide 3: November
Activities | Time
Preparation (Internal Meeting) D-Day 2 days in W1 of April 2018 (2-6 April) Venue Availability Participants Resource Person Budgets | W1-W2
TOR and Draft Provisional Agenda Preparation | W1-W4
Report the TOR and Provisional Agenda to SOM | W4

## Slide 4: December
Activities | Time
Invitation to NCC Indonesia for December’s Coordination | W1-W2
Confirmation from NCC Indonesia | W2-W3

## Slide 5: January
Activities | Time
Coordination Meeting With NCC Indonesia D-Day 2 days in W1 of April 2018 (2-6 April) Venue Availability Participants Resource Person Budgets | W1 – W2
Finalize TOR and Provisional Agenda | W2- W3
Save The Date Circular Letter (4-6 April 2018) Confirmation To Resource Person | W2 – W4
Reserve Venue | 

## Slide 6: February
Activities | Time
Formal Invitation Letter to Participants, Resource Person | W1
Drating and Finalizing Contract for Resource Person,DOI technical Assistance and other needed support person | W1-W4
RSVP for Participants | W2-W4

## Slide 7: March
Activities | Time
RSVP For Participants | W1
Reminder Letter | W2
Lodging, Event Logistics, Printing and Copies, Goody Bags, etc | W3-W4

## Slide 8: April
Activities | Time
Arrival of Participants,etc | 2-3 April
Event | 4-5 April : Meetings and PPP Task Force Establishment 6 April :Field Visit to MMAF Facilities
Departure of Participants, | 7 April

## Slide 9: Post Event Follow-up
Activities | Time
Quarterly Report to USDOI | W2 April –End of Quarter 3 (June)
Circulate Thank you letter and Meeting report (MoM,Photos) | W4 April